## Sheet1
RECALL TEAM AND PRELIMINARY STEPS
Actions | Initiated | Completed | Not done | Date | Initial
Recall team selected and organized |  | X |  | 07/22/2017
Recall Coordinator selected |  | X |  | 07/22/2017
Outside experts, consultant interviewed |  | X |  | 07/22/2017
Outside experts, consultant hired |  | X |  | 07/22/2017
Phone list given to all team members |  | X |  | 07/22/2017
Team Spokeperson selected and trained |  | X |  | 07/22/2017
Comminicate with department managers about plan & recall |  | X |  | 07/22/2017
Recall team tour company's facilities & customer sites and make recommendation |  | X |  | 07/22/2017
Prioritize risks and finidings from tour as 'high', 'medium' or 'low' |  | X |  | 07/22/2017
Solicit suggestions for improvements |  | X |  | 07/22/2017
Assess employee and department manager morale, commitment to improvemet |  | X |  | 07/22/2017
FDA or FSIS, pertinent local laws & guideline reviewed |  | X |  | 07/22/2017
-Product tracking system reviewed |  | X |  | 07/22/2017
-For receiving |  | X |  | 07/22/2017
-For manufacturing |  | X |  | 07/22/2017
-For distribution |  | X |  | 07/22/2017
Approve templates of letters, news releases, other documents |  | X |  | 07/22/2017
Internal contact list prepared |  | X |  | 07/22/2017
Customer/consignee contact list made |  | X |  | 2017-10-06
Create scenario & rules for Mock Recall |  | X |  | 2017-09-05
Mock Recalll exercise performed (See recall plan for procedures) |  | X |  | 2017-10-05
Recall Plan Modified as necessary |  | X |  | 07/23/2017
Legal Review of final plan |  | X |  | 07/23/2017
RECALL DISCOVERY PHASE
Action | Initiated | Completed | Not done | Date | Initial
Customer, Supplier , laboratory results, regulatory agencies , employee notified the problem |  | X |  | 07/24/2017
Complaint Investigation completed |  | X |  | 07/26/2017
Advises and recommendations from Scientific and Quality Assurance given |  | X |  | 07/26/2017
Laboratory tests and risk evaluations performed |  | X |  | 07/27/2017
Root cause identified |  | X |  | 07/27/2017
RECALL DECISION
Action | Initiated | Completed | Not done | Notes | Initial
Recall Team notified of problem |  | X |  | 07/22/2017
Recall Team briefed by legal counsel/ attorney |  | X |  | 07/22/2017
Department mangers briefed on problem and asked for input |  | X |  | 07/22/2017
FDA or FSIS rules reviewed |  | X |  | 07/22/2017
Department managers submit records to Team |  | X |  | 07/22/2017
Risk evaluated |  | X |  | 07/22/2017
Decision made to initiate a: |  | X |  | 07/22/2017
-Stock recovery |  | N/A |  | N/A
-Market Withdrawal |  | N/A |  | N/A
-Product Recall |  | X |  | 07/22/2017
If decision is internal, FDA or FSIS is notified |  | X |  | 07/22/2018
Team Spokesperson prepared information for public release |  | X |  | 07/23/2017
Team and legal counsel approves information for public release |  | X |  | 07/23/2017
IMMEDIATE ACTIONS
Action | Initiated | Completed | Not done | Date | Initial
Recall coordinator notified regulatory agency (ODA/FDA) |  | X |  | 07/23/2017
24-HOUR-ALERT submitted to the ODA/FDA |  | X |  | 07/23/2017
ATTACHMENT B initiated by the Recall Coordinator |  | X |  | 07/23/2017
Reportable Food Registry (RFR) filed ( for Class I recall only) |  | X |  | 07/23/2017
Product production halted |  | X |  | 07/23/2017
Product in warehouse secured |  | X |  | 07/23/2017
Receptionists, admins briefed on what to tell incoming callers & what info obtain from them |  | X |  | 07/23/2017
Update website with recall info |  | X |  | 07/23/2017
INFORMATION GATHERED
Action | Initiated | Completed | Not done | Date | Initial
Identify of product |  | X |  | 07/23/2017
Establish use of reworked or blended ingredeints & thier suppliers |  | X |  | 07/23/2017
Product package size(s) |  | X |  | 07/23/2017
Product code number(s) |  | X |  | 07/23/2017
Production dates |  | X |  | 07/23/2017
Quantity per Code Date |  | X |  | 07/23/2017
Quantity in controlled warehouses |  | X |  | 07/23/2017
Quantity shipped to customers |  | X |  | 07/23/2017
Quantity unaccounted for |  | X |  | 07/23/2017
Products under company's controls detained and segregated in isolated warehouse |  | X |  | 07/23/2017
PRODUCT LOCATION(S) DETERMINDED
Action | Initiated | Completed | Not done | Date | Initial
Location of each shipment established |  | X |  | 07/23/2017
Quantity shipped to each location verified |  | X |  | 07/23/2017
Quantity of product unaccounted for |  | X |  | 07/23/2017
Product distrinution list prepared |  | X |  | 07/23/2017
RECALL CLASSIFICATION AND DEPTH
Action | Initiated | Completed | Not done | Date | Initial
Recall Classification assigned by the lead agency |  | X |  | 07/23/2017
Recall Number(s) assigned by the lead agency |  | X |  | 07/23/2017
Depth of Recall(either established by the lead agency or determined by Recall Team) |  | X |  | 07/23/2017
Document templates revised to reflect current situation, recall classification&depth |  | X |  | 07/23/2017
Department managers updated about recall classification and depth |  | X |  | 07/23/2017
NOTIFICATION TO OUTSIDE GROUPS
Action | Initiated | Completed | Not done | Date | Initial
Wholesale distributors notified by phone/fax |  | X |  | 07/23/2017
Wholesale distributors notifed by mail |  | X |  | 07/23/2017
Retailers notified by phone/fax |  | X |  | 07/23/2017
Retailer notified by mail |  | X |  | 07/23/2017
FDA or FSIS aproves new release copy |  | X |  | 07/23/2017
News releases sent to media list such as AP news, etc |  | X |  | 07/23/2017
New releases sent to other pertinent contacts |  | X |  | 07/23/2017
Sales representatives instructed on Recall procedures |  | X |  | 07/23/2017
Point-of-sale information prepared for Sale representatives to deliver to retail customers |  | X |  | 07/23/2017
Continue to update Website as needed |  | X |  | 07/23/2017
PRODUCT DISPOSITION
Action | Initiated | Completed | Not done | Date | Initial
Company and lead agency agreed on collection and disposition of the products |  | X |  | 07/23/2017
Decision made about refund and exchage policies |  | X |  | 07/23/2017
Wholesaler informed of product disposition |  | X |  | 07/23/2017
Sales representatives assist consumers in complying with recall |  | X |  | 07/23/2017
Customer Service briefed on refund policy |  | X |  | 07/23/2017
Warehouse prepared to receive products |  | X |  | 07/23/2017
All received recall product recorded |  | X
Warehouse isolating returned products |  | X |  | 07/23/2017
Volume of recalled product produced with the volume of recalled product on hand and returned reconciled |  | X |  | 07/23/2017
Worked with ODA/FDA to determine re-condition or destruction plan |  | X |  | 07/23/2017
Re-conditioning plan submitted |  | X |  | 07/23/2017
Destruction plan submitted |  | X |  | 07/23/2017
Product destroyed or re-conditioned and witnessed by ODA/FDA |  | X |  | 07/23/2017
EFFECTIVENESS CHECKS
Action | Initiated | Completed | Not done | Date | Initial
FDA Effectiveness Check Level established |  | X |  | 07/24/2017
Effectiveness Checks begin |  | X |  | 07/24/2017
Effectiveness Checks Communication Log made |  | X |  | 07/24/2017
Finish date established |  | X |  | 07/24/2017
Review/evaluate Effectiveness Checks |  | X |  | 07/24/2017
Prepare Effectiveness Checks Summary |  | X |  | 07/24/2017
RECALL TERMINATION
Action | Initiated | Completed | Not done | Date | Initial
Team undertakes review of recall |  | X |  | 07/24/2017
Recall officially concluded |  | X |  | 07/26/2017
Restoration plan presented to the Senior Management and Recall Team |  | X |  | 07/26/2017
All corrective Action(s) taken |  | X |  | 07/26/2017
FDA or FSIS notified of Recall completion |  | X |  | 07/27/2017
Team receive written confirmation from FDA or FSIS of recall completion |  | X |  | 07/27/2017
Annoucement (and thanks, as needed) to customers about succesful end of recall |  | X |  | 07/27/2017
Update website; notify news media for follow up if necessary |  | X |  | 07/27/2017